## CDRL
| PLEASE SELECT Scope of supply: | [5 empty] | Milestone plan | [13 empty] | Supplier |  |  | [Supplier Name]
[7 empty] | Milestone applicable [Y/N] | [13 empty] | CAGE |  |  | [Supplier NATO Cage Code]
| Design & Production | [5 empty] | Planned date | [13 empty] | Part no / Rev. |  |  | [P/N on KONGSBERG contract/ purchase order]
[7 empty] | Planned location | [13 empty] | Part Title |  |  | [Part Name on KONGSBERG contract/ purchase order]
| Supplier Quality Assurance Requirement (SQAR) |  | Scope of Supply |  |  |  | Ref. or tailoring | Data deliverable |  |  | Contract Award (CA) | Design & Development Milestones |  |  |  |  | Prod. & Support Milestones |  |  |  | Data Use |  |  | Data deliverable clarification and comments
CDRL Item # | P10098 Rev. J Clause # | Requirement/ Data Deliverable | Design & Production | Built to Print | Services | Maintenance | - Template or DID (Data Item Description) - Tailoring description (e.g. SoW, SSS, HRS) | Document ID | Rev. | Owner |  | SRR/ SDR | PDR | CDR | TRR | FCA | PRR | FAI/ PCA | FAT | SAT | KONGSBERG Concurrence | Baseline | Frequency
C-001 | 1.2 | SQAR Compliance Matrix | D | D | D | D | KDA-TMPL-0210 |  |  | S |  | P | F | [7 empty] | Y | Y |  | Completed SQAR Compliance Matrix
C-002 | 4.2.4 | Supplier Conduct Principles | D | D | D | D | [5 empty] | F | [8 empty] | Y | N |  | Signed SCP. Supporting business conduct policies and procedures.
C-003 | 4.4.1 | Certification | D | D | D | D | [5 empty] | F | [8 empty] | N | N |  | ISO certificate. QAPP or SQAR Compliance Matrix as applicable. Other relevant certificates
C-105 | 8.1.2.6.3 | Change request submittal | D | D | D | D | BLA-6167 |  |  | S | [10 empty] | Y | N |  | Change request as applicable
C-151 | 8.1.2.9 | Configuration status accounting (CSA) | D | D | N/A | D |  |  |  | S | [10 empty] | Y | N |  | CSAR reporting as applicable if defined in the contract/ purchase order
C-152 | 8.1.3 | Product Safety | D | O | N/A | N/A |  |  |  | S |  |  | P | F | [6 empty] | Y | Y |  | Product safety documentation as applicable
C-153 | 8.1.3.1 | Restrictions of Hazardous Substances (RoHS) | D | D | N/A | N/A | [6 empty] | P | F | [6 empty] | Y | Y |  | Hazardous material list, including non-RoHS substances considered hazardous by the design authority
C-154 | 8.1.3.2 | Hazardous Sources | D | D | N/A | N/A | [6 empty] | P | F | [6 empty] | Y | Y |  | Documented information on Hazard sources not covered by RoHS
C-155 | 8.1.3.3 | Registration, Evaluation, Authorization and Restrictions of Chemicals (REACH) | D | D | N/A | N/A | [6 empty] | P | F | [6 empty] | Y | Y |  | Documented information on products containing substances found in the referenced candidate list
C-002 | 8.1.5 | Program Management Plan (PMP) | D | D | N/A | N/A |  |  |  | S |  | P | F | [7 empty] | Y | Y |  | PMP, QAPP or SQAR Compliance Matrix as applicable.
C-106 | 8.1.7 | Obsolescence / Last Time Buy (LTB) notfication | D | D | N/A | D | BLA-6167 |  |  | S | [10 empty] | Y | N |  | Last time buy proposal as applicable
C-110 | 8.3.3.1 | System Requirements Review (SRR) | O | N/A | N/A | N/A |  |  |  | S |  | F | [8 empty] | Y | N |  | SRR Report upon request
C-111 | 8.3.3.2 | System Design Review (SDR) | O | N/A | N/A | N/A |  |  |  | S |  | F | [8 empty] | Y | Y |  | SDR Report, incl. Functional baseline (FBL) upon request
C-112 | 8.3.4.1 | Preliminary Design Review (PDR) | O | N/A | N/A | N/A |  |  |  | S |  |  | F | [7 empty] | Y | N |  | PDR Report upon request
C-113 | 8.3.4.2 | Critical design review (CDR) | O | N/A | N/A | N/A |  |  |  | S |  |  |  | F | [6 empty] | Y | Y |  | CDR Report, incl. Allocated baseline (ABL) upon request
C-114 | 8.3.5.1 | Test Readiness Review (TRR) | O | O | O | O |  |  |  | S |  |  |  |  | F | [5 empty] | Y | N |  | Test Readiness Report upon request
C-115 | 8.3.5.2 | Functional Configuration Audit (FCA) | O | N/A | N/A | N/A |  |  |  | S | [5 empty] | F |  |  |  |  | Y | N |  | FCA Report upon request
C-150 | 8.3.5.3 | Design and Development Verification | D | N/A | N/A | N/A | e.g. KDA-TMPL-0189 |  |  | S |  |  | P |  |  | F |  |  |  |  | Y | Y |  | Verification Cross Reference Matrix (VCRM) or similar to be provided as agreed
C-116 | 8.5.1.7 | Production Readiness Review (PRR) | O | O | N/A | O | [10 empty] | F |  |  |  | Y | N |  | PRR Report upon request
C-117 | 8.5.1.8 | First Article Inspection (FAI) | O | O | O | O | e.g. AS9102 | [10 empty] | F |  |  | Y | N |  | FAI Report, incl. Contractual/ Product Baseline (CBL/PBL) upon request
C-118 | 8.5.1.9 | Physical Configuration Audit (PCA) | O | O | N/A | O | [11 empty] | F |  |  | Y | N |  | PCA Report upon request
C-119 | 8.5.1.10 | Factory Acceptance Test (FAT) | D | D | N/A | N/A |  |  |  | S |  |  |  |  | P |  |  |  | F |  | Y | Y |  | Factory Acceptance Test (FAT) Procedure and Report
C-120 | 8.5.1.11 | System Acceptance Test (SAT) | D | D | N/A | N/A |  |  |  | S |  |  |  |  | P |  |  |  |  | F | Y | Y |  | System Acceptance Test (SAT) Procedure and Report
C-201 | 8.5.7.1.1 | Failure Mode, Effect and Criticality Analysis (FMECA) | D | N/A | N/A | N/A |  |  |  | S |  |  | P | [7 empty] | N | N |  | Applicable FMEA/ FMECA deliverables to be specified in the CDRL
C-202 | 8.5.7.1.2 | Reliability Analysis | D | N/A | N/A | N/A |  |  |  | S |  |  | P | [7 empty] | N | N |  | Applicable reliability deliverables to be specified in the CDRL
C-203 | 8.5.7.1.3 | Life Limited Items (LLI) | D | N/A | N/A | N/A |  |  |  | S |  |  | P | F | [6 empty] | N | N |  | Documented information on Life Limited Items
C-204 | 8.5.7.2 | Maintenance Plan | D | N/A | N/A | N/A |  |  |  | S |  |  | P | [7 empty] | N | N |  | Product maintenance plan
C-205 | 8.5.7.3 | Technical manuals | D | N/A | N/A | N/A |  |  |  | S |  |  | P | [7 empty] | N | N |  | Operator and maintenance manuals
C-206 | 8.5.7.4 | Spare parts list | D | N/A | N/A | N/A |  |  |  | S |  |  | P | [7 empty] | Y | N |  | Spare Parts List
C-207 | 8.5.7.5 | Packing, handling, storage and transportation | D | D | D | D |  |  |  | S |  |  |  | P |  |  |  | F |  |  | N | N |  | Shipment documentation
C-208 | 8.5.7.6 | Tools and test equipment | D | D | D | D |  |  |  | S |  |  | P |  |  |  | F |  |  |  | N | N |  | Tools and Test Equipment List
C-100 | 8.6.1 | Certificate of Conformance | D | D | D | D |  |  |  | S | [7 empty] | F |  |  | N | N |  | CoC with each shipment
C-101 | 8.6.4 | Acceptance Data Package (ADP) | D | D | D | D | [11 empty] | F |  |  | Y | N |  | Available for each shipment/ source inspection
C-102 | 8.7.1 | Product nonconformity | D | D | D | D | BLA-6167 |  |  | S | [10 empty] | Y | N |  | Request for deviation or waiver as applicable
C-103 | 8.7.3 | Replaced components list | O | O | N/A | O |  |  |  | S | [10 empty] | N | N |  | As appropriate for repair, rework or maintenance
C-104 | 10.2.1.1 | Root Cause Analyses (RCA) | O | O | O | O |  |  |  | S | [10 empty] | Y | N |  | RCA Report as appropriate
| Other Contractual Data Requirements |  | D
| Doc./Cls # | Data Deliverable
C-1nn | e.g SOW 12.1 | e.g. Setting-to-work procedure | D
C-1nn | e.g. HRS 4.3.2 | e.g. Mechanical interface control drawing | D
CDRL Identifier
| Number | Category | Deliverable Identifier | [8 empty] | Deliverable Data Status Identifier
| C-001 - 099 | Administrative/Management Data | D - Document required |  |  |  |  | K - KONGSBERG |  |  |  | P - Preliminary
| C-100 - 199 | Engineering Data | N/A - Not Applicable |  |  |  |  | S - SUPPLIER |  |  |  | F - Final
| C-200 - 299 | Logistics Data | T - Tailored by KONGSBERG
O - Optional (TBD by KONGSBERG)
KONGSBERG PROPRIETARY. This document and its accompanying elements, contain KONGSBERG information which is proprietary and confidential. Any disclosure, copying, distribution or use is prohibited if not otherwise explicitly agreed with KONGSBERG in writing. Any authorized reproduction, in whole or in part, must include this legend. © 2016-2019 KONGSBERG – All rights reserved. KDA-TMPL-0187 Rev.D
Note on Z10: Barheim, Erlend: Any deliverable with a "Y" in this coloumn becomes part of the contractual baseline when approved.

## Contractual Baseline (hidden)
Doc. No. | Description | Rev. | CDRL | Resp. | Type of Documents required
TBA | Kongsberg/FLIR Contract |  |  | KDA | Contract
P10098 | Quality Assurance Requirements for Subcontractors | E | Ref. | KDA | Quality Requirements
A106503 | Marking Requirements | E |  | KDA | Marking Requirements
A123696 | Identification and Control of Hazardous Materials | - |  | KDA | Safety
SSS-60219558 | FLIR V1700 SA Specification | - | Yes | KDA | Technical Specification
SCD-68111320 | Specification Control Drawing - Heavy Duty Valve Cap |  |  | KPS | Drawing
SWQ-10032 | Quality Assurance Compliance Matrix |  |  | FLIR | Quality Compliance
PM504027 | Compliance Matrix to SSS for V1700 SA |  |  | FLIR | Technical Compliance
PE G009000 | Factory Acceptance Test Procedure (FAT) |  | Yes | FLIR | Test Procedure
PP G009000 | Factory Acceptance Test Report (ATR) |  |  | FLIR
PM504011 | Product Qualification Plan |  |  | FLIR
PM504012 | Product Qualification Report |  |  | FLIR
TBA | FLIR List of Hazardous Materials (A123696 response) |  |  | FLIR
PM503924 | Suppliers List V1700SA |  |  | FLIR
AD G009000 | Assembly Drawing V1700 SA |  |  | FLIR
PM504033 | Source Data for Technical Manuals |  |  | FLIR
ST G009000 | Structure & Inspection Plan | 1.0A |  | FLIR | Traceability
RS IDD-G009000 | Interface Design Description, FLIR V1700 SA (IDD)
TBD | Reliability Prediction (MTBF & FMECA)
TBD | Software Version Description - SVD
TBD | Software Test Report - STR
MD G009000 | V1700SA Basic Interface Drawing